## Planning
|  | Game: | BREVIK
|  | Team Members: | Karolina Kostrubiec
Jagoda Gniadek
| Task category | Task name | Task description | Difficulty level [1-3] | Assigned to | Progress [none ¦ in progress ¦ done] | End date
1 | Must have | MOVING | user moves | 1 | Jagoda, Karolina | done
2 |  | COLLECTING ITEMS | user collects items and move them to inventory | 2 | Jagoda | none
3 |  | COLLECTING EVIDENCES | displays prompts which help in solving the mystery | 2 | Jagoda | none
4 |  | EXPERIENCE | works like lives | 2 | Karolina | none
5 |  | STORY | introduce plot | 1 | Jagoda | none
6 |  | HIGHSCORES | shows highscores | 2 | Karolina | none
1 | Should have | COLLECTING ITEMS EXTRA | displays inventory | 2 | Jagoda | none
2 |  | COLLECTING EVIDENCES EXTRA | displays log with clues | 2 | Jagoda | none
3 |  | FOOLPROOF | detects stupid | 2 | Karolina | none
4 |  | TIMER | counts time | 1 | Karolina | none
5
6
1 | Nice to have | YOUR BOSS IS A D**K | if user doesn’t collect enough evidences in certain time, will lose experience | 3 | Jagoda | none
2 |  | ENEMIES | can shoot you | 3 | Karolina | none
3 |  | EXPERIENCE EXTRA | other special way to loose experience | 3 | Jagoda | none
4
5
6